## Sprint 1
Task | Orig. Est. | Cur. Est. | Effort | Remain | Responsible | Product Owner | Scrum Master | Team Members
Backend service and database for basic login | 4 | 4 | 4 | 0 | Ostap Malanyak | Ostap Malanyak | Viktoria Pernkopf | Audrey Wimmer
Frontend and routes for basic login | 3 | 12 | 12 | 0 | Antonio Petrov |  |  | Antonio Petrov
Backend service and database for meals | 5 | 6 | 6 | 0 | Ostap Malanyak
Frontend and routes for adding a meal | 3 | 10 | 10 | 0 | Audrey Wimmer
Backend service and database for room view | 4 | 2 | 2 | 0 | Viktoria Pernkopf
Frontend and routes for room view | 3 | 5 | 5 | 0 | Viktoria Pernkopf
Set up project structure | 0 | 3 | 3 | 0 | Viktoria Pernkopf
Set up database | 0 | 3 | 3 | 0 | Viktoria Pernkopf
Configure server | 0 | 6 | 6 | 0 | Viktoria Pernkopf
Design | 0 | 2 | 2 | 0 | Audrey Wimmer
Login testing | 0 | 0.5 | 0.5 | 0 | Ostap Malanyak
Meal adding testing | 0 | 0.5 | 0.5 | 0 | Ostap Malanyak
Room view testing | 0 | 0.5 | 0.5 | 0 | Viktoria Pernkopf
Total | 22 | 54.5 | 54.5 | 0 | -
User | Total
Ostap Malanyak | 11
Viktoria Pernkopf | 19.5
Audrey Wimmer | 12
Antonio Petrov | 12

## Sprint 2
Task | Orig. Est. | Cur. Est. | Effort | Remain | Responsible | Product Owner | Scrum Master | Team Members
Login hashing and salting | 2 | 2 | 2 | 0 | Antonio Petrov | Antonio Petrov | Audrey Wimmer | Viktoria Pernkopf
Cookies for account | 2.5 | 3 | 3 | 0 | Antonio Petrov |  |  | Ostap Malanyak
Add possibility to delete your account | 3 | 3 | 3 | 0 | Antonio Petrov
Add a log out button | 3 | 0.5 | 0.5 | 0 | Antonio Petrov
Adding new properties to user | 4 | 1 | 1 | 0 | Viktoria Pernkopf
Adding profile page | 4 | 3 | 3 | 0 | Viktoria Pernkopf
Add functionality for editing an existing meal | 2 | 2 | 2 | 0 | Viktoria Pernkopf
Calendar design for room view | 4 | 4.5 | 4.5 | 0 | Audrey Wimmer
Room backend | 4 | 3 | 3 | 0 | Ostap Malanyak
Create room frontend | 3 | 3 | 3 | 0 | Ostap Malanyak
Edit room frontend | 1 | 1 | 1 | 0 | Ostap Malanyak
Delete room frontend | 1 | 1 | 1 | 0 | Ostap Malanyak
Room overview | 3 | 3 | 3 | 0 | Audrey Wimmer
Invite functionality | 3 | 2 | 2 | 0 | Ostap Malanyak
Control access to pages if not logged in | 2 | 1 | 1 | 0 | Audrey Wimmer
Add error page | 1 | 1 | 1 | 0 | Ostap Malanyak
Unit tests | 2 | 2 | 2 | 0 | Viktoria Pernkopf
Total | 44.5 | 36 | 36 | 0 | -
User | Total
Ostap Malanyak | 11
Viktoria Pernkopf | 8
Audrey Wimmer | 8.5
Antonio Petrov | 8.5

## Sprint 3
Task | Orig. Est. | Cur. Est. | Effort | Remain | Responsible | Product Owner | Scrum Master | Team Members
Login hashing and salting | 2 | 2 | 2 | 0 | Antonio Petrov | Audrey Wimmer | Ostap Malanyak | Viktoria Pernkopf
Cookies for account | 5 | 5 | 5 | 0 | Antonio Petrov |  |  | Antonio Petrov
Display information when meal clicked | 1 | 3 | 3 | 0 | Antonio Petrov
Fix account deleting | 1 | 2 | 2 | 0 | Antonio Petrov
Improve room overview | 2 | 3 | 3 | 0 | Audrey Wimmer
Improve calendar design for room view | 4 | 5 | 5 | 0 | Audrey Wimmer
Manage room members | 3 | 2 | 2 | 0 | Audrey Wimmer
Delete room frontend | 2 | 2 | 2 | 0 | Ostap Malanyak
Edit room frontend | 3 | 4 | 4 | 0 | Ostap Malanyak
Improve create room frontend | 2 | 2 | 2 | 0 | Ostap Malanyak
Update product backlog | 1 | 1 | 1 | 0 | Ostap Malanyak
Effort plan | 2 | 1 | 1 | 0 | Viktoria Pernkopf
Unit tests | 1 | 1 | 1 | 0 | Viktoria Pernkopf
Basic recipe creation and overview | 3 | 4 | 4 | 0 | Viktoria Pernkopf
When adding a meal specify a recipe | 2 | 3 | 3 | 0 | Viktoria Pernkopf |  |  | x`
Add responsible logic to select user | 2 | 3 | 3 | 0 | Viktoria Pernkopf
Total | 36 | 43 | 43 | 0 | -
User | Total
Ostap Malanyak | 9
Viktoria Pernkopf | 12
Audrey Wimmer | 10
Antonio Petrov | 12

## Sprint 4
Task | Orig. Est. | Cur. Est. | Effort | Remain | Responsible | Product Owner | Scrum Master | Team Members
Ingredients on recipes and room | 4 | 8 | 8 | 0 | Ostap Malanyak | Audrey Wimmer | Ostap Malanyak | Viktoria Pernkopf
Confirm whether meal has been cooked | 3 | 3 | 3 | 0 | Audrey Wimmer |  |  | Antonio Petrov
Meal time validation | 2 | 3 | 3 | 0 | Audrey Wimmer
Manage room style | 1 | 2 | 2 | 0 | Audrey Wimmer
Subscribe to meal | 4 | 6 | 6 | 0 | Antonio Petrov
Fix account deleting | 1 | 2 | 2 | 0 | Antonio Petrov
Ingredient list functionality | 3 | 3 | 3 | 0 | Ostap Malanyak
Meals overview | 3 | 5 | 5 | 0 | Viktoria Pernkopf
Create invite links | 2 | 2 | 2 | 0 | Antonio Petrov
Create api proxy | 3 | 3 | 3 | 0 | Viktoria Pernkopf
Total | 26 | 37 | 37 | 0 | -
User | Total
Ostap Malanyak | 11
Viktoria Pernkopf | 8
Audrey Wimmer | 8
Antonio Petrov | 10

## Sprint 5
Task | Orig. Est. | Cur. Est. | Effort | Remain | Responsible | Product Owner | Scrum Master | Team Members
Add possibility to create own ingredients | 3 | 4 | 4 | 0 | Antonio Petrov | Ostap Malanyak | Viktoria Pernkopf | Antonio Petrov
Make ingredients group up in calendars | 2 | 2 | 2 | 0 | Viktoria Pernkopf |  |  | Audrey Wimmer
Make ingredients update when meals are added in calendars | 3 | 2 | 2 | 0 | Ostap Malanyak
Improve style to match other element items | 4 | 5 | 5 | 0 | Viktoria Pernkopf
Add possibility to create own ingredients | 4 | 4 | 4 | 0 | Ostap Malanyak
Edit recipe matches create recipe | 4 | 3 | 3 | 0 | Audrey Wimmer
Better view of recipes, ingredients and cooking steps | 2 | 1.5 | 1.5 | 0 | Antonio Petrov
Fix recipe lookup | 1 | 1 | 1 | 0 | Viktoria Pernkopf
Confirm whether meal has been cooked | 3 | 3 | 3 | 0 | Audrey Wimmer
Instead of the word profile put the profile picture | 2 | 1 | 1 | 0 | Audrey Wimmer
User navigation menu when clicked on profile picture | 2 | 2 | 2 | 0 | Audrey Wimmer
Change names of frontend services to "name-frontend-service" | 1 | 1 | 1 | 0 | Antonio Petrov
Unify styling | 4 | 3 | 3 | 0 | Viktoria Pernkopf
Make ingredients be assignable to individual users | 2 | 2 | 2 | 0 | Viktoria Pernkopf
Bought ingredients or not | 4 | 5 | 5 | 0 | Antonio Petrov
Improve meal management view | 3 | 3 | 3 |  | Antonio Petrov
Marking removes ingredients | 3 | 3 | 3 | 0 | Ostap Malanyak
Past ingredients unaccountable | 2 | 2 | 2 | 0 | Audrey Wimmer
Update ReadMe | 1 | 1 | 1 | 0 | Ostap Malanyak
Unit tests | 1 | 1 | 1 | 0 | Viktoria Pernkopf
Total | 28 | 26.5 | 26.5 | 0 | -
User | Total
Ostap Malanyak | 10
Viktoria Pernkopf | 14
Audrey Wimmer | 11
Antonio Petrov | 14.5