## Backlog - Total
Title | URL | Assignees | Status | Parent issue | Sub-issues progress | Labels | Milestone
Set up project structure | https://github.com/vikipernkopf/room-food/issues/23 | vikipernkopf | Done | https://github.com/vikipernkopf/room-food/issues/29 |  | configuration | Sprint 1
Set up initial database | https://github.com/vikipernkopf/room-food/issues/28 | Awimmer2 | Done | https://github.com/vikipernkopf/room-food/issues/29 |  | configuration | Sprint 1
Configure server | https://github.com/vikipernkopf/room-food/issues/37 | vikipernkopf | Done | https://github.com/vikipernkopf/room-food/issues/29 |  | configuration | Sprint 1
Backend service and database for basic login | https://github.com/vikipernkopf/room-food/issues/15 | ostapmalanyak | Done | https://github.com/vikipernkopf/room-food/issues/2 |  | new feature | Sprint 1
Frontend and routes for basic login | https://github.com/vikipernkopf/room-food/issues/17 | Antonio040 | Done | https://github.com/vikipernkopf/room-food/issues/2 |  | new feature | Sprint 1
Login testing | https://github.com/vikipernkopf/room-food/issues/45 | ostapmalanyak | Done |  |  | testing | Sprint 1
Backend service and database for meals | https://github.com/vikipernkopf/room-food/issues/18 | ostapmalanyak | Done | https://github.com/vikipernkopf/room-food/issues/9 |  | new feature | Sprint 1
Basic frontend and routes for adding a meal | https://github.com/vikipernkopf/room-food/issues/19 | Awimmer2 | Done | https://github.com/vikipernkopf/room-food/issues/9 |  | new feature | Sprint 1
Meal adding testing | https://github.com/vikipernkopf/room-food/issues/46 | ostapmalanyak | Done |  |  | testing | Sprint 1
Backend service and database for room view | https://github.com/vikipernkopf/room-food/issues/21 | vikipernkopf | Done | https://github.com/vikipernkopf/room-food/issues/3 |  | new feature | Sprint 1
Frontend and routes for beta room view | https://github.com/vikipernkopf/room-food/issues/20 | vikipernkopf | Done | https://github.com/vikipernkopf/room-food/issues/3 |  | new feature | Sprint 1
Room view testing | https://github.com/vikipernkopf/room-food/issues/47 | vikipernkopf | Done |  |  | testing | Sprint 1
Basic design | https://github.com/vikipernkopf/room-food/issues/72 | Awimmer2 | Done | https://github.com/vikipernkopf/room-food/issues/9 |  | new feature | Sprint 1
Initial configuration | https://github.com/vikipernkopf/room-food/issues/29 | vikipernkopf | Done |  | 3 / 3 (100%) | configuration | Sprint 1
Create a basic login | https://github.com/vikipernkopf/room-food/issues/2 | Antonio040, ostapmalanyak | Done | https://github.com/vikipernkopf/room-food/issues/4 | 2 / 2 (100%) | new feature | Sprint 1
Create a basic add meal functionality | https://github.com/vikipernkopf/room-food/issues/9 | Awimmer2, ostapmalanyak | Done | https://github.com/vikipernkopf/room-food/issues/3 | 3 / 3 (100%) | new feature | Sprint 1
Create a basic page for a room view | https://github.com/vikipernkopf/room-food/issues/3 | vikipernkopf | Done |  | 3 / 3 (100%) | new feature | Sprint 1
Update product backlog | https://github.com/vikipernkopf/room-food/issues/90 | ostapmalanyak | In Progress | https://github.com/vikipernkopf/room-food/issues/87 |  | documentation | Sprint 2
Effort plan | https://github.com/vikipernkopf/room-food/issues/31 | vikipernkopf | In Progress | https://github.com/vikipernkopf/room-food/issues/87 | 0 / 0 (0%) | documentation | Sprint 2
Accpetance criteria | https://github.com/vikipernkopf/room-food/issues/88 | ostapmalanyak | In Progress | https://github.com/vikipernkopf/room-food/issues/87 |  | documentation | Sprint 2
Test plan | https://github.com/vikipernkopf/room-food/issues/89 | Antonio040, Awimmer2 | In Progress | https://github.com/vikipernkopf/room-food/issues/87 |  | documentation | Sprint 2
Login hashing and salting | https://github.com/vikipernkopf/room-food/issues/78 | Antonio040 | Todo | https://github.com/vikipernkopf/room-food/issues/4 |  | enhancement | Sprint 2
Cookies for account | https://github.com/vikipernkopf/room-food/issues/79 | Antonio040 | Todo | https://github.com/vikipernkopf/room-food/issues/4 |  | new feature | Sprint 2
Add possibility to delete your account | https://github.com/vikipernkopf/room-food/issues/80 | Antonio040 | Todo | https://github.com/vikipernkopf/room-food/issues/4 |  | new feature | Sprint 2
Add a log out button | https://github.com/vikipernkopf/room-food/issues/81 | Antonio040 | Todo | https://github.com/vikipernkopf/room-food/issues/4 |  | new feature | Sprint 2
Adding new properties to user | https://github.com/vikipernkopf/room-food/issues/84 | vikipernkopf | Todo | https://github.com/vikipernkopf/room-food/issues/10 |  | enhancement | Sprint 2
Adding profile page | https://github.com/vikipernkopf/room-food/issues/85 | vikipernkopf | Todo | https://github.com/vikipernkopf/room-food/issues/10 | 0 / 0 (0%) | new feature | Sprint 2
Add functionality for editing an existing meal | https://github.com/vikipernkopf/room-food/issues/82 | vikipernkopf | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Calendar design for room view | https://github.com/vikipernkopf/room-food/issues/24 | Awimmer2 | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | enhancement | Sprint 2
Room backend | https://github.com/vikipernkopf/room-food/issues/91 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Create room frontend | https://github.com/vikipernkopf/room-food/issues/92 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Edit room frontend | https://github.com/vikipernkopf/room-food/issues/93 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Delete room frontend | https://github.com/vikipernkopf/room-food/issues/94 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Room overview | https://github.com/vikipernkopf/room-food/issues/95 | Awimmer2 | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Invite functionality | https://github.com/vikipernkopf/room-food/issues/13 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/5 |  | new feature | Sprint 2
Control access to pages if not logged in | https://github.com/vikipernkopf/room-food/issues/86 | Awimmer2 | Todo | https://github.com/vikipernkopf/room-food/issues/97 |  | enhancement | Sprint 2
Add error page | https://github.com/vikipernkopf/room-food/issues/96 | ostapmalanyak | Todo | https://github.com/vikipernkopf/room-food/issues/97 |  | new feature | Sprint 2
Unit tests | https://github.com/vikipernkopf/room-food/issues/83 | vikipernkopf | Todo | https://github.com/vikipernkopf/room-food/issues/44 |  | testing | Sprint 2
Documentation | https://github.com/vikipernkopf/room-food/issues/87 | Antonio040, Awimmer2, ostapmalanyak, vikipernkopf | Todo |  | 0 / 4 (0%) | documentation | Sprint 2
Login and sign up | https://github.com/vikipernkopf/room-food/issues/4 | Antonio040 | Todo |  | 1 / 5 (20%) | enhancement, new feature | Sprint 2
Profile functionality | https://github.com/vikipernkopf/room-food/issues/10 | Antonio040, vikipernkopf | Todo |  | 0 / 2 (0%) | enhancement, new feature | Sprint 2
Room functionality | https://github.com/vikipernkopf/room-food/issues/5 | Awimmer2, ostapmalanyak | Todo |  | 0 / 8 (0%) | new feature | Sprint 2
Create a page for all avaliable rooms | https://github.com/vikipernkopf/room-food/issues/6 |  | In Planning |  |  | new feature
Database for storing recipes | https://github.com/vikipernkopf/room-food/issues/16 |  | In Planning | https://github.com/vikipernkopf/room-food/issues/14 |  | new feature
Room manager view | https://github.com/vikipernkopf/room-food/issues/12 |  | In Planning |  | 0 / 0 (0%) | new feature
Create a "New recipe" pop up | https://github.com/vikipernkopf/room-food/issues/22 |  | In Planning | https://github.com/vikipernkopf/room-food/issues/8 |  | new feature
Recipe lookup | https://github.com/vikipernkopf/room-food/issues/14 |  | In Planning | https://github.com/vikipernkopf/room-food/issues/8 | 0 / 1 (0%) | new feature
Recipe functionality | https://github.com/vikipernkopf/room-food/issues/8 |  | In Planning | https://github.com/vikipernkopf/room-food/issues/7 | 0 / 2 (0%) | new feature
Ingredient list functionality | https://github.com/vikipernkopf/room-food/issues/7 |  | In Planning |  | 0 / 1 (0%) | new feature